## Sheet1
|  | Arfat Kamal |  |  |  | Md Saidur Rahman |  |  |  | Sahat al Ferodus Fahim |  |  |  | Tasawar Siddiquy
Tasks | Short summary | To-do | Deadline | Status | Completion Date | To-do | Deadline | Status | Completion Date | To-do | Deadline | Status | Completion Date | To-do | Deadline | Status | Completion Date
Task 1 | 1. SysML Diagrams | Use case | 2022-04-03 | Completed | 2022-04-03 | Requirements | 2022-04-03 | Completed | 2022-04-03 | Block-Diagrams | 2022-04-03 | Completed | 2022-04-01 | Scenarios | 2022-04-03 | Completed | 2022-04-02
[10 empty] | Constraints | 2022-04-03 | Completed | 2022-04-02 | Constraints | 2022-04-03 | Completed | 2022-04-02
Task 2 | 1. Run the system in simulation. 2. Run the code on lab presented dummy robot | Motor | 2022-04-10 | Completed | 2022-04-05 | IR sensor | 2022-04-10 | Completed | 2022-04-07 | White_line_implentation | 2022-04-10 | Completed | 2022-04-07 | Ultrasonic | 2022-04-10 | Completed | 2022-04-07
[6 empty] | Circuit Dev | 2022-04-10 | Completed | 2022-04-07 | Black_line_implentation | 2022-04-10 | Completed | 2022-04-07
[10 empty] | State_chart |  | Completed | 2022-04-07
Task 3 | 1. 3D Design. 2. Prepare parts for laser cut and 3D printer. 3. Assemble all the parts. |  |  |  |  | Design motor holder | 2022-05-01 | Completed | 2022-05-01 | Design robot sturcture | 2022-04-14 | Completed | 2022-04-14 | Design ultrasonic holder | 2022-05-01 | Completed | 2022-05-01
[10 empty] | Prepare all the parts for laser | 2022-05-01 | Completed | 2022-05-01